April 2026 — November 2027

Global AI Index

Work Plan

Measuring global generative AI adoption across six phases, from foundation through launch and post-publication.

Prepared for Technical Committee Review · April 2026

OVERVIEW

# Measuring Global Generative AI Adoption

This draft work plan covers the full project lifecycle for the Global AI Index — from governance formation through publication and post-launch monitoring. It is organized across six phases spanning April 2026 to November 2027. It is subject to change as the project progresses.

Decision points, Roundtable meetings, and launches are called out throughout. Each decision gate requires specified inputs and delivers a go/no-go decision by the designated owner. If consensus fails at a TC-owned decision, the Terms of Reference require escalation to the Roundtable.

# Project Phases

| Phase | Title | Dates | Description |
| --- | --- | --- | --- |
| Phase 1 | Foundation April – June 2026 G | overnance setup, TC meeting sc | hedule set up, MDLA signings, API Data Framework drafting, Commitment signings by 6/3. |
| Phase 2 | Stakeholder Design Inputs July | – September 2026 MDLA roster | expansion, starter stakeholder consultations for design inputs, API synthetic data encryption test, Metric Harmonization Framework drafting. |
| Phase 3 | Design October – December 2026 | Consumer Chat Framework, glob | al researcher consultation, Metric Harmonization Retreat |
| Phase 4 | Prototype January – April 2027 | Metric Harmonization Framewor | k, US Adaptation Evaluation, Technical Specs, Data Sharing Protocols, Data Encryption and Transfer documentation, closed pilot with real data, Roundtable review at Spring Meetings, first Iteration produced. |
| Phase 5 | Iterate, Review, & Launch May | – July 2027 Formal company rev | iew window, final legal clearance, pre-publication sign-off, stakeholder consultations, joint launch at 2027 Global AI Summit. |
| Phase 6 | Post-Launch August – November | 2027 Stakeholder feedback, sec | ond-quarter data ingestion, Q3 indicator release, joint think pieces and data stories, Grant Completion Report. |

Legend Decision Gate Roundtable Meeting Major Launch / Milestone

| Code | Description |
| --- | --- |
| C1 | Publication & Comms |
| C2 | Consumer Chat Global Indicators |
| C3 | Consumer Chat Users and Use Metric Harmonization |
| C4 | US Adaptation |
| C5 | Sector-Specific Indicators |
| C6 | API Global Indicators |
| C7 | API Users and Use Metric Harmonization |
| C8 | Research |

| Month | Governance & Roundtable | Legal & MDLA | Stakeholder Engagement | Adoption Indicators(C2, C4, C6) | Users and Use Harmonization(C3, C7) | Research & Supplemental(C5, C8) | Publication & Comms(C1) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 — FoundationApril – June 2026 |  |  |  |  |  |  |  |
| Apr2026 | Roundtable • AI Roundtable (4/16) • Updated Milestone Mapping • TC: Commitments, Work Planning • Commitment commenting period opens (4/27) | • MDLA signed (4/16) | — | — | — | — | — |
| May2026 | • TC: API Data Framework | • MDLA negotiations • Consultant and Researcher Contracting | • Stakeholder consultation protocol finalized | • API Data Framework (TC drafting) | • API Data Framework (TC drafting) | • Research partner scoping: Stanford HAI, MS AIEI, MIT FutureTech | — |
| Jun2026 | Decision Point 1 • Commitment signings (6/3 DDP Annual Meetings) • TC: API Data Framework | • Commitment signings (6/3) • MDLA signings • MDLA Schedules: API | • US: Human Services & Safety Net Consultation Report | • API Data Framework finalized • Secure data transfer and aggregation protocol design review - API tokens | • API Data Framework finalized • Secure data transfer and aggregation protocol design review - API metrics - industry, time of day, agentic, etc. | — | • Quarterly Progress Report Q2 |
| Phase 2 — Stakeholder Design InputsJuly – September 2026 |  |  |  |  |  |  |  |
| Jul2026 | • TC: API Synthetic Data Test | • Outstanding MDLA escalation | • US: Workforce Training Consultation Report • Global: Agriculture Consultation @ ICAS Report | • Synthetic Data Test of data transfer and aggregation protocol - API metrics | • Synthetic Data Test of data transfer and aggregation protocol - API metrics | • Framework for Labor Exposure Index by Country Income — Needed Inputs for Monitoring | — |
| Aug2026 | • TC: Metric Harmonization Framework | • MDLA status review | • Global: Digital Health & EdTech Consultation Report • US: Labor Organization Consultation Report | — | • Users and Use Metric Harmonization Framework (drafting) • Topic taxonomies, sampling, labor/industry classifications | — | — |
| Sep2026 | Decision Point 2 • MDLA roster adequacy review • TC: Metric Harmonization, | • Confirm minimum viable data contributor roster | • US: K-12 + Post-Secondary Consultation Report • Global: Macro/Fiscal Consultation Report | • | • Harmonization retreat prep; pre-read distributed • | • US Stakeholder Engagement Synthesis Report (internal) • Global Stakeholder Engagement Synthesis Report (internal) • Low-Resource Language Index Draft | • Quarterly Progress Report Q3 |
| Phase 3 — DesignOctober – December 2026 |  |  |  |  |  |  |  |
| Oct2026 | Roundtable + Gate 3 • Roundtable check-in (virtual) • Commitment 5 proceed / modify / stop • Commitment 8 scope review • Final MDLA escalation: any outstanding contributors | — | • Global Researcher Consultation (MS AIEI) & Synthesis Report • Metric Harmonization Retreat Stakeholder Sessions | — | • Sector-Specific Scope Proposals • Metric Harmonization Retreat Technical Sessions(informed by agreed frameworks, completed research, stakeholder synthesis reports, sector-specific scope proposals, and MDB/UN scope discussions) | — | — |
| Nov2026 | • TC: Consumer Chat; Metric Harmonization Testing • Commence Global Firm Outreach (India, China, France, etc.) | • MDLA Consumer Chat Schedules | — | • Consumer Chat Framework finalized • Secure data transfer and aggregation protocol design review - Consumer Chat | • Harmonization Testing Coordination I | • AR Monitoring Framework • Consumer Chat and API Normalization and Benchmark Datasets | — |
| Dec2026 | • TC: Consumer Chat Synthetic Data Test; Consumer Chat Data Aggregation and Transfer Method | — | — | • Synthetic Data Test of data transfer and aggregation protocol - Consumer Chat • Data Aggregation & Transfer Method Documentation (draft) | • Harmonization Testing Coordination II | • ASR Monitoring Framework | • Quarterly Progress Report Q4 |

| Month | Governance & Roundtable | Legal & MDLA | Stakeholder Engagement | Adoption Indicators(C2, C4, C6) | Users and Use Harmonization(C3, C7) | Research & Supplemental(C5, C8) | Publication & Comms(C1) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 4 — PrototypeJanuary – April 2027 |  |  |  |  |  |  |  |
| Jan2027 | • TC: Metric Harmonization, Open Source Trends, Index Construction Methodology | • MDLA Conversation and API Metric Data Schedules | — | • Index Construction & Methodology (C2, C6) • Dry-run: first synthetic end-to-end submission | • Harmonization Testing Coordination III • Metric Harmonization Framework finalized (C3, C7) | • Open Source Trends Monitoring Framework | • Publication Framework (draft) |
| Feb2027 | • TC: US Adaptation, Technical Specs Documentation | • MDLA Conversation and API Metric Data Schedules • Additional Global Firm MDLAs | • US Stakeholder Consultation on Draft US Adaptation Assessment | • US Adaptation Assessment (C2, C4, C6) • Technical Specs Documentation (C2, C4, C6) • Data Aggregation and Transfer Method (C2, C4, C6) • Data Sharing Protocols finalized | • US Adaptation Assessment (C3, C4, C7) • Technical Specs Documentation (C3, C7) • Data Aggregation and Transfer Method (C3, C7) • Data Sharing Protocols finalized | • Stakeholder Synthesis Report | • Launch comms strategy kick-off • Publication Framework (draft) |
| Mar2027 | • TC: Prototype, Supplemental Indicators, Sector-Specific Indicator Derivations | — | — | • Closed pilot with real data • PROTOTYPE ready | • Closed pilot with real data • PROTOTYPE ready | • ASR Model Diffusion & Intensity metrics • Bot Economy API Measurement Research • Combined data and policy interactive dashboard prototype | • Publication Framework finalized • Partner co-promotion coordination begins |
| Apr2027 | Roundtable • Roundtable Prototype Review (Spring Meetings) | — | — | • FIRST ITERATION | • FIRST ITERATION | • AR Device Sales & Penetration Metrics • Global AI Skills Supply & Demand Index • Open Source Model Trends | • Launch comms plan finalized • Media & embargo strategy |
| Phase 5 — Iterate, Review, & LaunchMay – July 2027 |  |  |  |  |  |  |  |
| May2027 | • TC: Review | • Formal company review & approval window (all contributors, 4 wks) • Final stakeholder validation | • MDB partner pre-publication data review (post-MDLA clearance, confidential) • AfDB, ADB, IDB, EBRD review regional outputs under Development Data Partnership data access rights • Findings inform final revisions prior to Decision Gate 4 sign-off | • First Iteration — company redlines | • First Iteration — company redlines | • First Iteration — company redlines | • Speaker prep, press kit, embargo mgmt. • Publication Framework finalized |
| Jun2027 | Decision Point 4 • Pre-publication final sign-off | • Final legal clearance per MDLA review rights | • Pre-Launch US-Stakeholder Convening & Discussion of Post-Launch joint publications | • Revision (buffer for slippage) | • Revision (buffer for slippage) | — | • Final comms rehearsal • Summit logistics |
| Jul2027 | LAUNCH | LAUNCH | LAUNCH | LAUNCH | LAUNCH | LAUNCH | • LAUNCH at 2027 Global AI Summit (Switzerland) • Publication + media rollout • Interactive website and partner links |
| Phase 6 — Post-LaunchAugust – November 2027 |  |  |  |  |  |  |  |
| Aug2027 | • TC: Consumer Chat; Metric Harmonization Testing | — | • Post-launch user feedback collection | • Second-quarter data ingestion | — | — | • Post-launch comms report |
| Sep2027 | • TC: Output Internal Review | — | • Q3 indicator release | — | — | • Joint Stakeholder short publications • Commissioned data stories and visualizations | • Quarterly Progress Report Q3 |
| Oct2027 | Roundtable • Roundtable Annual Meetings check-in | — | — | — | — | • Joint Stakeholder short publications • Commissioned data stories and visualizations | — |
| Nov2027 | — | — | — | — | — | • Grant Completion Report | — |

SECTION 3

# Decision Points

Four decision points are scheduled before launch. Each point requires the specified inputs and delivers a program-modification decision, as is needed.

If consensus fails at a TC-owned decision, the Terms of Reference require escalation to the Roundtable.

| Point | Timing | Decision | Inputs Required | Owner / Venue |
| --- | --- | --- | --- | --- |
| 1 | June 3, 2026 | Commitment signings by participating organizations | Finalized commitment text; leadership approvals from each participating org | DDP Annual Meetings |
| 2 | September 2026 | MDLA roster adequacy — proceed with Tech Specs on current contributor set, or delay | MDLA status for all participating companies; synthetic data test results | Technical Committee (escalate to Roundtable if no consensus) |
| 3 | October 2026 | Commitment 5 (Sector-Specific Policy Indicators) — proceed / modify / stop | TC-prepared final scope & terms; consolidated stakeholder consultation findings | Roundtable (per Commitment 5 text) |
| 4 | June 2027 | Pre-publication final sign-off on First Iteration outputs | All company reviews complete; legal clearance per MDLA; IGO co-publication approvals | Roundtable (virtual if needed) |

SECTION 4

# AI Roundtable Touchpoints

Roundtable oversight is distributed across the project rather than concentrated at start and end. Natural IMF/WBG venues are leveraged where possible to minimize scheduling burden.

| Date | Venue | Purpose |
| --- | --- | --- |
| April 16, 2026 | In-person, IMF / World Bank Group Spring Meetings | Inaugural Roundtable: review commitments, Technical Committee updates, Anthropic MDLA signing |
| October 2026 | Virtual | Decision Gate 3: Commitment 5 (Sector-Specific Policy Indicators) proceed / modify / stop. Check-in on MDLA roster, harmonization framework preview; review/approve TC's Commitment 8 (research) scope |
| April 2027 | In-person, IMF / World Bank Group Spring Meetings | Prototype review; approve First Iteration direction |
| June 2027 | Virtual (as needed) | Decision Gate 4: Pre-publication final sign-off |
| July 2027 | Global AI Summit, Switzerland | Joint publication launch |
| October 2027 | IMF / WBG Annual Meetings | Post-launch review, future roadmap |

SECTION 5

# Company Review & Approval Windows

The Participant Principles require each participating company to review and approve any output derived from its data before publication.

| Deliverable | Review Window | Duration | Notes |
| --- | --- | --- | --- |
| First Iteration (publication candidate) | May 2027 | 4 weeks | All participating companies review in parallel; redlines consolidated by DDP Secretariat |
| Final publication (post-revision) | Jun 2027 | 2 weeks | Confirmation that redlines are incorporated; Decision Gate 4 |